## 2023
PROJECT PLAN
PROJECT |  |  | START DATE
MAD Credentials |  |  | 2023-08-03 |  |  | <-- Enter initial Start Date to populate Timeline dates.
Users to complete non-shaded fields only. | [5 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
TASKS | TASK OWNER | STATUS | START DATE | END DATE | DAYS | 2023-07-31 | 2023-08-01 | 2023-08-02 | 2023-08-03 | 2023-08-04 | 2023-08-07 | 2023-08-08 | 2023-08-09 | 2023-08-10 | 2023-08-11 | 2023-08-14 | 2023-08-15 | 2023-08-16 | 2023-08-17 | 2023-08-18 | 2023-08-21 | 2023-08-22 | 2023-08-23 | 2023-08-24 | 2023-08-25 | 2023-08-28 | 2023-08-29 | 2023-08-30 | 2023-08-31 | 2023-09-01 | 2023-09-04 | 2023-09-05 | 2023-09-06 | 2023-09-07 | 2023-09-08 | 2023-09-11 | 2023-09-12 | 2023-09-13 | 2023-09-14 | 2023-09-15 | 2023-09-18 | 2023-09-19 | 2023-09-20 | 2023-09-21 | 2023-09-22 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | 2023-10-02 | 2023-10-03 | 2023-10-04 | 2023-10-05 | 2023-10-06 | 2023-10-09 | 2023-10-10 | 2023-10-11 | 2023-10-12 | 2023-10-13 | 2023-10-16 | 2023-10-17 | 2023-10-18 | 2023-10-19 | 2023-10-20 | 2023-10-23 | 2023-10-24 | 2023-10-25 | 2023-10-26 | 2023-10-27 | 2023-10-30 | 2023-10-31 | 2023-11-01 | 2023-11-02 | 2023-11-03 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-09 | 2023-11-10 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-16 | 2023-11-17 | 2023-11-20 | 2023-11-21 | 2023-11-22 | 2023-11-23 | 2023-11-24 | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-11 | 2023-12-12 | 2023-12-13 | 2023-12-14 | 2023-12-15 | STATUS
Objective 1: Project Kickoff |  |  | 2023-08-03 | 2023-08-10 | 6 |  |  |  | A | A | A | A | A | A | [91 empty] | Not Started
Define and schedule meeting cadence | McKenzie Day | Complete | 2023-08-03 | 2023-08-07 | 3 |  |  |  | A | A | A | [94 empty] | In Progress
Create Team and Project Plan | McKenzie Day | Complete | 2023-08-03 | 2023-08-10 | 6 |  |  |  | A | A | A | A | A | A | [91 empty] | Complete
Request Oracle Project Number | McKenzie Day | Complete | 2023-08-03 | 2023-08-04 | 2 |  |  |  | A | A | [95 empty] | On Hold
Identify stakeholders and create RACI | McKenzie Day and Project Sponsor | Complete | 2023-08-04 | 2023-08-10 | 5 |  |  |  |  | A | A | A | A | A | [91 empty] | Overdue
Objective 2: Credentialing Framework |  |  | 2023-08-09 | 2023-10-30 | 59 | [7 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | [34 empty] | Needs Update
Define common language | ID Team | Complete | 2023-08-09 | 2023-08-16 | 6 | [7 empty] | A | A | A | A | A | A | [87 empty] | Canceled
Outline program goals and value | ID Team | Complete | 2023-08-10 | 2023-08-16 | 5 | [8 empty] | A | A | A | A | A
Determine credential criteria | ID Team | Complete | 2023-08-16 | 2023-08-23 | 6 | [12 empty] | A | A | A | A | A | A
Determine how to verify proficiency | ID Team | Complete | 2023-08-16 | 2023-08-23 | 6 | [12 empty] | A | A | A | A | A | A
Create Mad Credentials Program Framework PPT/DOC | McKenzie Day | Complete | 2023-08-23 | 2023-09-29 | 28 | [17 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Present Mad Credentials Program Overview to stakeholders | McKenzie Day | Complete | 2023-10-02 | 2023-10-30 | 21 | [45 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Objective 3: Vendors and Tooling |  |  | 2023-09-06 | 2023-11-08 | 46 | [27 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Talk w/ IT Infrastructure about tooling | McKenzie Day | Complete | 2023-09-06 | 2023-09-13 | 6 | [27 empty] | A | A | A | A | A | A
Define vendor requirements and criteria | ID Team | Complete | 2023-09-13 | 2023-09-20 | 6 | [32 empty] | A | A | A | A | A | A
Write a list of questions for vendors | ID Team | Complete | 2023-09-20 | 2023-09-27 | 6 | [37 empty] | A | A | A | A | A | A
Create shortlist of vendors | McKenzie Day | Complete | 2023-09-27 | 2023-10-04 | 6 | [42 empty] | A | A | A | A | A | A
Kick-off vendor discussions and demos | McKenzie Day | Complete | 2023-10-04 | 2023-11-01 | 21 | [47 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Evaluate vendors and make final decision | ID Team | Complete | 2023-11-01 | 2023-11-08 | 6 | [67 empty] | A | A | A | A | A | A
Objective 4: Pilot |  |  | 2023-11-08 | 2023-12-29 | 38 | [72 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Talk w/ pilot stakeholders and make plan | McKenzie Day | Complete | 2023-11-08 | 2023-11-17 | 8 | [72 empty] | A | A | A | A | A | A | A | A
Pilot credentialing program with DataSwift product | ID Team | In Progress | 2023-11-17 | 2023-12-15 | 21 | [79 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Evaluate pilot and make recommendations | ID Team | Not Started | 2023-12-15 | 2023-12-29 | 11 | [99 empty] | A
Next Steps (Q1 2024):
Define key use cases
Engage in vendor procurement
Write program governance document
Finalize contract
Launch communications campaign